## Sheet1
Pre Production Phase
Date In Weeks | Ident Storyboarding | Advert Storyboarding | Project Planning | Git and Unity Set up | Asset Creation | Ident Pre Vis | Presentation Planning | RipReel | Pre Production Presentation
2016-11-03
2016-11-10
2016-11-17
2016-11-24
Production Phase
| Environment creation | Camera creation | UI and interface | Presentation planning | Asset Creation | Ident Final Creation | Advert first draft | Editing | Production 90 second timeline presentation
2016-12-01
2016-12-08
2016-12-15
2016-12-22
2016-12-29
2017-01-05
2017-01-12
2017-01-19
Post Production Phase
| Project finishing touches | Delivery | Advert Final | Editing | Voice over | Presentation Planning | Final Presentation
2017-01-26
2017-02-02
2017-02-09
2017-02-16
2017-02-23
2017-03-02
2017-03-09
2017-03-16
2017-03-23
2017-03-30